STAFF REPORT

DATE: 	June 12, 2012
TO: 		Honorable Members of the Visual Arts Committee

FROM: 	Jennifer Lovvorn

RE: 	Modification to Selection Process for new Subway Project Opportunities

BACKGROUND

At the May 2012 Visual Arts Committee, I presented the Detailed Public Art Project Outline for the following projects: Chinatown Station – Crosscut Cavern Wall; Moscone Station – Ticketing Hall Wall; Moscone Station – Entry Plaza Sculpture and Union Square Station – Elevator and Deck Glass. Those project outlines included descriptions of the opportunities, project budget allocations, selection processes and timelines.

The selection process described in these outlines included a national call to artists with all minimally qualified candidates being presented to the selection panel. According to procurement regulations associated with the Federal Transit Administration funding for the Central Subway Public Art Projects, staff is precluded from pre-screening the applicant pool to select the slate of appropriate candidates for review by the Selection Panel.

REQUESTED ACTION

In order to establish slates of appropriate candidates for each of the four unique project opportunities, staff proposes to include an additional panel review of all the applicants’ materials and qualifications. This additional selection panel would be comprised of three arts professionals. The role of the panel of arts professionals would be to review and score the applications and identify the short list of candidates for each of the four project opportunities. These slates of candidates would then be presented to the respective project selection panels and the selection process from this point on would follow the process as described in the Detailed Project Outlines, which were approved last month.

REVISED TIMELINE (Subject to change)

RFQ Posted/Advertised					June 20, 2012

RFQ Deadline							July 31, 2012

Arts Professional Panel Review				Early August 2012

Selection Panel Meeting #1 (Select Finalists)		Late August 2012

VAC Approval of Finalists					September 19, 2012

Finalist Orientation/Stakeholder Meeting			early October 2012

Proposal Deadline						November 19, 2012

Proposal Display						December 3 – 17, 2012

Selection Panel Meeting #2 (Review Proposals)		Early to mid-January 2013

VAC Approval of Project Artists/Proposals			January 2013

Artists under contract					February 2013

REQUEST FOR APPROVAL

At the June 20, 2012 Visual Arts Committee meeting, staff will request approval on the following consent calendar item:

Motion to approve a modification to the selection process and timeline to include a review by a panel of arts professionals of the applicants to the following new Central Subway public art projects: Chinatown Station – Crosscut Cavern Wall; Moscone Station – Ticketing Hall Wall; Moscone Station – Entry Plaza Sculpture and Union Square Station – Elevator and Deck Glass.

FURTHER INFORMATION

Contact Jennifer Lovvorn, Public Art Project Manager at (415)252-4637 or by email at jennifer.lovvorn@sfgov.org.