|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **(Group 1/ Issue 1)**  **(Problem or Improvement that needs to be addressed in the community)** | **Stakeholders**  **(People who need to be in the room)** | **Task of the Stakeholders**  **(Once in the room, what will be their contribute or task within the group)** | **Estimated Timeframe**    **(Concrete Goals that can be obtain in 6mos, 1 year, 18 mos, 3 years, 5+ years )** | **Accountability Partner**  **(This is the person/ organization who will have ownership to see this through) The 2+2+2+2= Rule**  **Pick two people, two organizations, two politicians, and two public forums )** |
| Substance Abuse- Specifically for Transitional Aged Youth (TAY) Population:  **Goals:**  1. Understanding What Drugs Are Being Abused?  2. New Interventions (Inclusive of TAY People with (criminal) history | DCYF  Community  TAY REP  DPH/ HSA  Service Providers | Develop Policy  Develop New Treatments  Adding Restorative Justice   * Victims * Families * Community   Host Focus Groups with Transitional Aged Youth Population | 1 to 3 years  Focus Group –(5) | **Person/ Politician**  People with Passion for this population  **Government department/Organization:**  Adult Probation Department  Department of Public Health    **Public Forum**  Health Commission |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **(Group 2/ Issue 1)**  **(Problem or Improvement that needs to be addressed in the community)** | **Stakeholders**  **(People who need to be in the room)** | **Task of the Stakeholders**  **(Once in the room, what will be their contribute or task within the group)** | **Estimated Timeframe**    **(Concrete Goals that can be obtain in 6mos, 1 year, 18 mos, 3 years, 5+ years )** | **Accountability Partner**  **(This is the person/ organization who will have ownership to see this through) The 2+2+2+2= Rule**  **Pick two people, two organizations, two politicians, and two public forums )** |
| Lack of Career Opportunities  **Goals:**  1. Actual Employment Pipeline Not Job Training  Example: San Mateo Model As Inspiration | OEWD  Labor Council  Trade Unions  City College  Private Sector companies  5 Keys  SFUSD  Project Rebound  SF Public Defender  SF District Attorney | \*Liaison  \*Commitment to hire  \*Expanding Capacity  \*Navigating Outreach  \* Funding for academic and career coaching and counseling  \*Books/ Fee and money assistance  \*Auto record clearance / expungement seal | Meeting to Build Coalition with Stakeholder= 6 Months  Secure Money  12 months to 18 months | **Person/ Politician**  Supervisor Walton  Supervisor Fewer  **Government department/Organization:**  Local 6  City College  **Public Forum**  City College Board of Trustees  Reentry Council |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **(Group 3/ Issue 1)**  **(Problem or Improvement that needs to be addressed in the community)** | **Stakeholders**  **(People who need to be in the room)** | **Task of the Stakeholders**  **(Once in the room, what will be their contribute or task within the group)** | **Estimated Timeframe**    **(Concrete Goals that can be obtain in 6mos, 1 year, 18 mos, 3 years, 5+ years )** | **Accountability Partner**  **(This is the person/ organization who will have ownership to see this through) The 2+2+2+2= Rule**  **Pick two people, two organizations, two politicians, and two public forums )** |
| Mental Health Treatment for people discharged from custody (even if no criminal charges are filled) | \*DPH  \*Sheriff’s Department  \*Adult Probation \*Department  \*District Attorney  \*Public Defenders  (PRU unit)  \*Community Organizations like RAMS and NAMI  \*Board of Supervisors  \*Governor and State Legislative (members)  \*HSA | \***DPH tasks:** Provide treatment (need more of it)  **\*Sheriff’s Task**:Up training (to connect people to treatment also)  \***APD’s Task:** Provide treatment or connect people to treatment  **\*District Attorney Task:** more focus on treatment rather than punishment/ criminal charges  **\*Public Defender Task**: PRU unit to help connect people to services  **\*CBO Task:** Provide Treatment  \***BOS Task**: Get more treatment facilities  **\*HSA-Task:** Make sure incarcerated folks don’t lose funds or Medi-Cal. | 1- 4years | **Person/ Politician**  N/A    **Government department/Organization:**  Public Defender  **Public Forum**  Human Service Commission  Reentry Council  Board of Supervisors |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **(Group 4/ Issue 1)**  **(Problem or Improvement that needs to be addressed in the community)** | **Stakeholders**  **(People who need to be in the room)** | **Task of the Stakeholders**  **(Once in the room, what will be their contribute or task within the group)** | **Estimated Timeframe**    **(Concrete Goals that can be obtain in 6mos, 1 year, 18 mos, 3 years, 5+ years )** | **Accountability Partner**  **(This is the person/ organization who will have ownership to see this through) The 2+2+2+2= Rule**  **Pick two people, two organizations, two politicians, and two public forums )** |
| 24-7 Crisis Center | Peers  Clinicians  Law Enforcement (SFPD)  CBOs, DPH, HSA,  Justice Partners (APD, PD, Courts, DA, Sheriff, SFPD) | Peers Tasks:   * Support * De-escalation * First Response * Develop response   Clinicians Tasks:   * Develop Model * Triage   Law Enforcement Task:   * Trained in Crisis | Mini Plan  2 months identifying  Menu of Services  Pilot to build out existing infrastructure | **Person/ Politician**  Mayor London Breed  Supervisor Fewer  Supervisor Haney    **Government department/Organization:**  UCSF Citywide  Department of Public Health  **Public Forum**  Reentry Council  Safety and Justice Challenge Forum |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **(Group 5/ Issue 1)**  **(Problem or Improvement that needs to be addressed in the community)** | **Stakeholders**  **(People who need to be in the room)** | **Task of the Stakeholders**  **(Once in the room, what will be their contribute or task within the group)** | **Estimated Timeframe**    **(Concrete Goals that can be obtain in 6mos, 1 year, 18 mos, 3 years, 5+ years )** | **Accountability Partner**  **(This is the person/ organization who will have ownership to see this through) The 2+2+2+2= Rule**  **Pick two people, two organizations, two politicians, and two public forums )** |
| Reentry Navigation Center  **Goal:**  Coordinating Law Enforcement Offices  Supporting Late Night Releases | Department of Homelessness and Supportive Housing (HSH)  Mayor’s Office  Board of Supervisors (BOS)  Justice Partners’ (APD, PD, Courts, DA, Sheriff, and SFPD) | HSH Task:  Buy-in with the Center  Mayor’s Office Task:  Funds and Support  BOS Task: Funds and Support  Justice Partners Task: Shared Big Picture Vision | 30/ 60/ 90 Check-ins then go to quarterly meeting | **Person/ Politician**  N/A  **Government department/Organization:**  APD  Sheriff  DPH  **Public Forum**  N?A |